## Summary
Transport-You API
Development Task Tracker
Live follow-up of completed and pending work. Update the Task Tracker tab; these totals recalc automatically.
Overview | How to use
Total tasks | • Edit only the Task Tracker tab.
Completed | • Status: pick Completed or Pending (dropdown).
Pending | • Priority: High / Medium / Low / - (dropdown).
Progress | • Fill Owner and Target Date as you assign work.
• Green = Completed, Amber = Pending (auto).
Pending by priority | • This Summary recalculates from those cells.
High
Medium
Low

## Task Tracker
ID | Module / Feature | Category | Description | Status | Priority | Owner | Target Date | Notes
1 | Authentication | Auth | Register, login, logout, current-user; email OTP verify & resend. | Completed | - |  |  | Laravel Passport OAuth2.
2 | Tenant onboarding | Tenancy | Self-service operator onboarding endpoint. | Completed | -
3 | Tenant profile | Tenancy | View & update authenticated tenant (logo, details). | Completed | -
4 | Locations | Reference | CRUD for terminals/locations (state + city). | Completed | -
5 | States | Reference | Reference CRUD for states. | Completed | -
6 | Routes | Reference | CRUD + route resolver (id / location ids / city names). | Completed | -
7 | Vehicle categories | Fleet | Global reference CRUD (super-admin). | Completed | -
8 | Vehicle classes | Fleet | Reference CRUD. | Completed | -
9 | Seat arrangement types | Fleet | Catalogue: name, seats, image, desc; filter by vehicle type; diagram images. | Completed | -
10 | Vehicle types | Fleet | CRUD; many-to-many seat arrangements with one default. | Completed | -
11 | Vehicles | Fleet | CRUD for physical vehicles. | Completed | -
12 | Schedules - one-off | Scheduling | Create concrete dated trip (+ optional round trip). | Completed | -
13 | Schedules - recurring | Scheduling | Create single recurring pattern; no per-day rows. | Completed | -
14 | Derived capacity | Scheduling | Capacity & seat map derive from seat arrangement. | Completed | -
15 | Seat selection toggle | Scheduling | Per-schedule flag enabling seat picking. | Completed | -
16 | Trip search (public) | Trips | Merge concrete + virtual recurring occurrences by date-in-interval. | Completed | -
17 | Seat status endpoint | Trips | Available/unavailable map for schedule or recurring occurrence. | Completed | -
18 | Booking module | Booking | Passenger details + conditional seat selection; capacity/clash checks; round trips. | Completed | -
19 | Recurring materialisation | Booking | Booking a recurring day find-or-creates the concrete trip. | Completed | -
20 | Scheduled trips module | Scheduling | List/filter, show + manifest, status, cancel (cascades bookings). | Completed | -
21 | Image upload | Platform | Upload endpoint for vehicle / arrangement images. | Completed | -
22 | Automated tests | QA | Feature suite: 78 passing. | Completed | - |  |  | 3 pre-existing unrelated failures.
23 | Payments | Payments | Gateway integration & pay-for-booking flow. | Pending | High |  |  | Payment model exists, unused.
24 | Booking confirmation | Payments | Auto-confirm booking on payment; expire unpaid holds. | Pending | High
25 | Seat hold / locking | Booking | Short-lived reservation + row locking vs double-booking. | Pending | High |  |  | Currently validation-in-transaction only.
26 | Tickets | Booking | Issue tickets (QR/reference) per passenger after payment. | Pending | High |  |  | Ticket model exists, unused.
27 | Notifications | Platform | Email/SMS: OTP, confirmations, reminders, cancellations. | Pending | High
28 | Driver & vehicle assignment | Ops | Assign physical vehicle + driver to a scheduled trip. | Pending | Medium
29 | Driver management | Ops | Driver records, availability, assignment. | Pending | Medium
30 | Manifest module | Ops | Standalone manifest generation/export. | Pending | Medium |  |  | Partial view on scheduled-trip show.
31 | Recurring pattern management | Scheduling | List/edit/delete recurring patterns endpoints. | Pending | Medium
32 | Recurring round-trip pairing | Trips | Pair outbound + return recurring occurrences in search. | Pending | Medium
33 | RBAC permissions | Platform | Granular roles/permissions enforcement. | Pending | Medium |  |  | Role/Permission models exist.
34 | Fix pre-existing tests | QA | Auth OTP response & Route state_id not-null. | Pending | Medium |  |  | Unrelated to new work.
35 | Promotions / discounts | Marketing | Promo codes, fare discounts. | Pending | Low |  |  | Promotion model exists, unused.
36 | Loyalty program | Marketing | Points accrual/redemption. | Pending | Low |  |  | LoyaltyTransaction model exists, unused.
37 | Refunds & policies | Payments | Refund handling & cancellation policy engine. | Pending | Low
38 | Reporting & analytics | Analytics | Operator dashboards: sales, occupancy, revenue. | Pending | Low
39 | API documentation | Docs | Published OpenAPI/Swagger or Postman collection. | Pending | Low